## QUICK REFERENCE – WHAT TO SEND WHEN

### Email #1 (First Outreach)

Subject: "Expanding Behavioral Health Care in [City/Region]" Attach: One-Page Summary (PDF) Body: Brief intro + key statistic + link to Prospectus + calendar link for discovery call

### Email #2 (Follow-up, no response Week 1)

Subject: "IHEP: Behavioral Health Integration for [Organization]" Attach:Prospectus (PDF) Body: More personalized + market stat + call to action with calendar link

### Discovery Call (Week 1)

Prepare: One-Pager + Pitch Deck (have visible during call) Present: Slide deck (15–20 min) + discuss prospectus + intro to Six-Step Process Close: If mutual interest, send complete Six-Step Guide + schedule Step 2

### Step 2 Discovery (Week 2–3)

Send: Complete Six-Step Guide + Technical Architecture overview + FAQPurpose: Partner team reviews in preparation for deep-dive assessments

### Step 3 Compliance (Week 4+)

Send: Compliance Toolkit (templates, checklists, sample agreements) Purpose:Legal team uses for DSA/BAA negotiation

### Step 4 Technical Planning (Week 6+)

Send: Technical Architecture Document (full) + Training Curriculum outline + Implementation Runbook outline Purpose: IT and clinical teams begin planning

### Step 5 Pilot Launch (Week 12)

Send: Complete Training Curriculum + Implementation Runbook (full) + Outcome Measurement Dashboard + Weekly status template Purpose: Operational execution and measurement

### Ongoing (Month 4+)

Send monthly: Outcome dashboard; Send quarterly: Outcome report + business review materials Purpose: Sustain partnership, track performance, plan growth

## HOW TO USE THIS DOCUMENT

### For IHEP Leadership

- Use Sections 1–4 as master reference for all partner conversations

- Use Section 5 for consistency in what/when to send materials

- Update monthly with new FAQs, case studies, lessons learned

### For Partner Prospects

- Start with Section 2 (One-Pager) for quick overview

- Read Section 1 (Prospectus) for comprehensive understanding

- Use Section 3 (FAQ) to answer specific questions

- Reference Section 4 (Six-Step Guide) to understand implementation path

### For Implementation Teams

- Use Section 4 (Six-Step Guide) as master project plan

- Use Section 5 (Distribution) to know what materials to send at each stage

- Update Section 3 (FAQ) monthly with new questions from partners

- Reference Sections 1 & 2 to refresh on value proposition

## SUCCESS METRICS

### Track These

- Materials downloads: Which are most popular?

- Conversion rate: % of prospects who download prospectus → request discovery call → become partners

- Time to partnership: How long from first contact to signed agreement?

- Partner satisfaction: Ask at key milestones: "Which materials were most helpful?"

- Implementation efficiency: Are partners completing each step on the projected timeline?

### Feedback Loop

- After each partnership decision (go/no-go): Ask partner which materials influenced decision

- After each step: Ask IHEP team which materials were hardest to explain; update for clarity

- Monthly: Update FAQ with new questions

- Quarterly: Refresh case studies with learnings

- Annually: Audit all materials for regulatory compliance

## CONTACT & SUPPORT

### Questions About IHEP?

- General partnership inquiries: [Contact info]

- Technical questions: [CIO/Solutions Architect contact]

- Clinical questions: [CMO contact]

- Compliance/legal questions: [Chief Compliance Officer contact]

### Document Information

- Created: January 8, 2026

- Version: 2.0 (Consolidated Master Document)

- Next Review: Q2 2026

- Format: Persistent doc artifact (does not expire)

This document consolidates all six IHEP materials into one searchable, downloadable, permanent reference. It can be saved, printed, shared, and referenced indefinitely without expiration.