## SIX-STEP APPLICATION PROCESS GUIDE

### Overview

6 steps spanning 4–6 months from initial interest to full-scale deployment:

- Interest & Initial Assessment (Weeks 1–2)

- Deep-Dive Discovery (Weeks 2–4)

- Compliance & Legal Review (Weeks 4–8)

- Technical Planning & Configuration (Weeks 6–12)

- Pilot Launch & Optimization (Weeks 12–24)

- Scale & Continuous Improvement (Month 4+)

### STEP 1: Interest & Initial Assessment (Week 1–2)

Objectives: Establish mutual interest, gather high-level info, confirm alignment, schedule deeper discovery.

Key Activities:

1.1 Partner Submits Inquiry

- Organization name, location, type (primary care, behavioral health, EHR vendor, health system)

- Contact: name, title, email, phone

- Key stakeholders: CEO, CMO, CIO, compliance officer

- Size: patient population, # of sites, current EHR

- Why IHEP? (2–3 sentences)

- Goals: expand capacity, improve outcomes, achieve integration certification

- Constraints: IT budget, legacy systems, regulatory concerns

1.2 IHEP Initial Screening (24–48 hours)

- Confirm receipt, assess completeness

- Assign IHEP partnership lead (VP Business Development or designee)

- Fit assessment: Alignment with vision? Red flags? Capacity to support?

- Decision: Go, No-Go (rare), or Conditional Go

1.3 Introductory Call (Week 1–2, 60 minutes)

- Participants: Partner (primary contact, CEO/EVP, CMO if applicable, CIO if applicable) + IHEP (partnership lead, CCO, CIO, compliance officer)

- Agenda:

  - IHEP overview: mission, evidence, CoCM, tech approach (10 min)

  - Partner deep dive: mission, challenges, why behavioral health now (15 min)

  - Strategic alignment: Do our goals align? Misalignments? (10 min)

  - Technical overview: Current EHR, interoperability efforts, IT capacity, constraints (15 min)

  - Timeline & next steps: If mutual interest, schedule discovery (10 min)

- Outcomes:

  - Both parties confirm mutual interest

  - IHEP lead + partner identify key stakeholders

  - Share: Prospectus, One-Pager, FAQ, Playbook, Technical Architecture overview

  - Go/No-Go decision: Proceed to deep-dive discovery?

### STEP 2: Deep-Dive Discovery (Week 2–4)

Objectives: Detailed technical, clinical, compliance assessment; identify gaps; develop roadmap; finalize decision to proceed.

Key Activities:

2.1 Technical Discovery Session (90 minutes)

- Participants: Partner (CIO, EHR admin, IT PM) + IHEP (CIO, Solutions Architect, Interop Specialist)

- Scope:

  - Current EHR: vendor, version, modules, go-live date, HL7 interfaces, API capabilities

  - Interoperability: existing HIE participation, APIs in use, MDM practices, patient identity matching

  - Proposed IHEP data flows: referral workflow, real-time vs. batch, scheduling integration, note sync, outcome data

  - Constraints: API rate limits, data residency, firewall configs, vendor restrictions, budget/timeline

- Deliverable: Technical Fit Assessment (3–5 pages) including: supported integration patterns, effort/timeline, recommended interop platforms, cost, risks, go/no-go

2.2 Clinical & Operational Discovery (90 minutes)

- Participants: Partner (CMO, CEO, practice manager, care team reps) + IHEP (CCO, Care Model Lead, Operations Manager)

- Scope:

  - Current behavioral health: # providers (FTE), psychiatrists, therapists, coordinators; wait times; psychiatric access; screening rates; referral patterns; population health metrics

  - Proposed CoCM: launch scope (single practice vs. multiple sites), target population (depression? anxiety? SUD? comorbidities), estimated patient volume (Month 1, 3, 12), staffing (hire new or dedicate existing), psychiatrist model (in-house, contract, telehealth)

  - Workflow integration: How are behavioral health concerns identified today? Proposed warm handoff? Documentation? Billing experience?

  - Clinical readiness: PCP team interest in CoCM? Experience with measurement-based care (PHQ-9, GAD-7)? Quality improvement culture?

  - Goals & metrics: Success in Month 3, 6, 12? KPIs (PHQ-9 reduction, ED visits, satisfaction, revenue)?

- Deliverable: Clinical Readiness Assessment including: current state vs. desired, staffing needs, process changes required, go/no-go recommendation

2.3 Compliance Discovery (120 minutes)

- Participants: Partner (Compliance officer, legal counsel, privacy officer, security officer, risk manager) + IHEP (Chief Compliance Officer, Counsel, CISO)

- Scope:

  - Current compliance: HIPAA status, recent audits, existing BAAs, consent management, RBAC, audit logging

  - 42 CFR Part 2 readiness (if applicable): Do you treat SUD patients? Federally assisted programs? Current understanding of Part 2? Existing infrastructure?

  - State obligations: Jurisdiction-specific privacy laws (PA Privacy Act, etc.)

  - Data security: Encryption, firewalls, antivirus, EDR, penetration testing, incident response, business continuity, cyber liability insurance

  - Vendor management: How do you vet and contract vendors? Existing BAA templates? SLA enforcement? Industry certifications?

  - IHEP-specific concerns: Multi-party consent language, telehealth psychiatry/DEA rules, Part 2 record handling, segmentation

- Deliverable: Compliance Gap Assessment including: current maturity, identified gaps, compliance roadmap, cost/timeline, go/no-go recommendation

2.4 Discovery Synthesis & Decision Gate (60 minutes)

- Participants: Partner (CEO, CMO, CIO) + IHEP (VP Business Development, CCO, CIO, Compliance Officer)

- Scope: Review all three assessments; integrated recommendation; go/no-go decision

- Outcomes:

  - GO: Proceed to compliance & legal review (Step 3)

  - CONDITIONAL GO: Resolve specific issues before proceeding

  - NO-GO: IHEP provides recommendations and alternative partnerships

### STEP 3: Compliance & Legal Review (Week 4–8)

Objectives: Finalize agreements, close compliance gaps, obtain executive sign-off.

Key Activities:

3.1 Legal & Compliance Workgroup Kickoff (60 minutes)

- IHEP provides: DSA template, BAA template, exhibits, Part 2 addendum (if applicable)

- Discuss: Partner legal requirements, modifications to templates, signature authority, board requirements, timeline

3.2 Data Sharing Agreement (DSA) Negotiation (Weeks 4–6)

- IHEP provides standard DSA; partner legal reviews and suggests edits

- IHEP responds to material requests within 5 business days

- Key provisions: data ownership, use restrictions, redisclosure controls, patient access rights, data deletion, liability, indemnification

- Deliverable: Fully executed DSA

3.3 Business Associate Agreement (BAA) & Technical Schedules (Weeks 5–7)

- IHEP provides BAA incorporating HIPAA Final Rule language

- Key provisions: HIPAA safeguards per 45 CFR §164.306, subcontractor management, audit rights, breach notification (24 hours), encryption (TLS 1.2+, AES-256), access controls (RBAC, MFA, audit logging)

- Part 2 Addendum (if applicable): SUD record segmentation, consent language, redisclosure restrictions, compliance monitoring

- Deliverable: Fully executed BAA with Technical Schedules & Exhibits

3.4 Compliance Roadmap Finalization (Weeks 6–8)

- IHEP develops checklist of compliance gaps from Step 2

- Prioritize: Critical (must fix before pilot), High/Medium (30 days post-launch)

- Examples: RBAC system, cyber liability insurance, updated privacy notice, Part 2 consent process, staff training

- Deliverable: Compliance Readiness Checklist with Gap Remediation Roadmap

3.5 Insurance & Vendor Risk Assessment (Weeks 5–8)

- Partner provides: Cyber liability insurance certificate

- IHEP provides: SOC 2 Type II audit, security questionnaire responses

- Mutual risk assessments completed; residual risks documented and accepted

- Deliverable: Vendor Risk Assessment Summary & Acceptance

3.6 Compliance Readiness Sign-Off

- Both parties confirm: DSA executed, BAA executed, Part 2 addendum (if applicable) executed, critical gaps remediated, insurance verified, vendor assessments accepted, compliance checklist signed

- Go-signal: Proceed to Step 4 (Technical Planning)

### STEP 4: Technical Planning & Configuration (Week 6–12)

Objectives: Configure interoperability, design consent/access controls, test workflows, prepare staff, finalize go-live plan.

Key Activities:

4.1 Technical Architecture Review & Finalization

- Confirm: Interop platform selection (1upHealth, Smartlink, NexHealth, HiXConnect), integration approach (FHIR vs. HL7 v2), batch vs. real-time, encryption standard

- Finalize data flows: inbound (EHR → IHEP), outbound (IHEP → EHR), bidirectional (scheduling, notes)

- Document: Data mappings, HL7 code systems, environment strategy (dev, QA, production)

4.2 Interoperability Platform Setup (Weeks 6–9)

- Provision interop instance; establish network connectivity

- Test EHR connectivity: API auth, data accuracy, latency

- Configure field mappings; test bidirectional data flow

- Harden security: TLS 1.2+, AES-256 encryption, audit logging

- Deliverable: Platform Configuration Checklist & Test Results

4.3 Consent & Access Control Design (Weeks 7–10)

- Design: Initial consent (PCP + behavioral health + IHEP), SUD consent (separate, narrower), telehealth consent

- RBAC: Patient, care manager, psychiatrist, PCP, admin, analytics (each with specific permissions)

- Enforcement: Database-level RBAC (not just UI); quarterly access reviews; immediate revocation upon staff departure

- Part 2 controls: SUD records marked with redisclosure restrictions; segmentation (optional)

- Deliverable: Consent & Access Control Specification

4.4 Test Environment Validation (Weeks 8–11)

- End-to-end workflow testing (non-PHI): registration, referral, assessment, scheduling

- Data quality validation: Sample records compared EHR ↔ IHEP; no data loss/corruption; acceptable latency

- Security & compliance testing: Encryption verified, access controls tested, audit logging validated, consent enforcement tested

- Error handling & failover: API failures, network outages, database failures tested

- Deliverable: Test Environment Validation Report & Sign-Off

4.5 Staff Training Plan & Materials (Weeks 8–12)

- Curriculum: Technical staff (system architecture, troubleshooting), clinical staff (workflows, assessments, documentation), admin staff (scheduling, billing), leadership (overview, metrics)

- Materials: Slide decks, job aids, videos, FAQ, escalation procedures

- Delivery: Group sessions (2–3 hours), hands-on lab (1 hour), self-paced modules, super-user training

- Support: Weekly office hours for 4 weeks post-launch

- Deliverable: Training Curriculum, Materials, Schedule

4.6 Implementation Runbook & Go-Live Checklist (Weeks 10–12)

- Runbook: Step-by-step startup, data migration, user provisioning, rollback, monitoring, daily ops

- Go-Live Checklist:

  - All contracts executed

  - Critical compliance gaps remediated

  - Interop platform configured & tested

  - EHR connectivity validated

  - Consent & access controls deployed & tested

  - All staff trained & assessed

  - Helpdesk & support processes documented

  - Contingency plans & rollback procedures ready

  - Data backup & disaster recovery tested

  - Executive sign-off on readiness

- Contingency planning: Identify highest-risk aspects, acceptable downtime, rollback timeline

- Deliverable: Implementation Runbook, Go-Live Checklist, Contingency Plan

### STEP 5: Pilot Launch & Optimization (Week 12–24)

Objectives: Go-live, validate workflows, measure outcomes, refine processes, build readiness for scale.

Key Activities:

5.1 Soft Launch (Weeks 12–14)

- Week 1: Go-live; daily stand-ups (15 min); monitor system performance (API uptime, data sync success, errors); collect staff feedback

- Weeks 2–3: Ramp enrollment from 50 to 75–100 patients; refine intake; conduct first psychiatrist consultations; publish "lessons learned" summary

5.2 Workflow Refinement (Weeks 14–20)

- On-site observations of care team workflows

- Interviews with PCP, care manager, psychiatrist, admin staff

- Identify bottlenecks, workarounds, positive surprises

- System adjustments: Reconfigure if workflows don't match; debug data sync; adjust access controls

- Clinical protocol refinement: Assess patient population, psychiatrist workload, outcomes, adjust care protocols

- Training booster sessions: "Lunch and learn" on specific topics

- Weekly/bi-weekly updates to partner leadership

5.3 Outcome Measurement (Weeks 14–24)

- Track all patients: baseline and follow-up (30, 60, 90 days)

- Primary outcome: PHQ-9 at baseline, 30, 60, 90 days

- Secondary: GAD-7, medication adherence, appointment adherence, NPS

- System outcomes: ED visits, inpatient admissions, acute care utilization (30–90 days pre vs. post)

- At 60-day mark: Analyze outcomes (% showing ≥50% PHQ-9 improvement, patterns, risks)

- Monthly dashboard to partner; quarterly formal outcome report

- Deliverable: Pilot Phase Outcome Report

5.4 Billing & Revenue Cycle Validation (Weeks 14–24)

- Confirm CPT codes configured (99492, 99493, 99494); validate billing logic; confirm diagnosis codes, modifiers

- First claims submitted Week 14–16; track acceptance/denial rates; analyze denial codes

- Revenue optimization: Address common denials, ensure documentation completeness, optimize payer selection

- Financial reconciliation: Compare projected vs. actual revenue; identify and address discrepancies

- Deliverable: Pilot Phase Revenue Cycle Report

5.5 Compliance Monitoring (Weeks 14–24)

- Monthly consent validation (all enrolled patients have valid, documented consent)

- Monthly access control audits (RBAC matches role; no inappropriate access)

- Data handling spot checks: 10–20 patient records audited for security, Part 2 compliance

- Breach monitoring: Watch for incidents; if occurs, follow breach response protocol

- Deliverable: Quarterly Compliance Monitoring Report

### STEP 6: Scale & Continuous Improvement (Month 4+)

Objectives: Expand to full patient population/additional sites, sustain outcomes, build long-term partnership.

Key Activities:

6.1 Scale Planning & Transition (Weeks 20–24)

- Pilot phase go/no-go decision: Met success criteria? Issues to resolve?

- Scale roadmap: Current practice (months 4–6), 2nd practice/site (months 5–8), 3rd+ and full expansion (months 8–12)

- Staffing plan: When hire additional care managers? Psychiatrist capacity?

- Financial sustainability: CPT realization rate? Risk contract opportunities? ED/inpatient savings quantified?

- Payer partnerships: Which payers are top revenue sources? Outreach for preferential reimbursement or risk contracts?

- Deliverable: Scale & Sustainability Plan

6.2 Continued Outcome Optimization (Ongoing)

- Monthly outcome dashboards (enrollment, PHQ-9 trends, utilization)

- Quarterly outcome reports with clinical and financial analysis

- Quarterly care team huddles to discuss outcomes, identify improvements

- A/B testing of care protocols

- Patient feedback loops → process improvements → re-measure outcomes

- Share wins with clinical teams and leadership

6.3 Compliance & Risk Management (Ongoing)

- Quarterly access control audits (100% review of user access)

- Semi-annual data security assessment (penetration testing, vulnerability scanning)

- Annual SOC 2 Type II audit for IHEP

- Monitor regulatory changes; update policies/controls as needed

- Annual breach response drills

- Annual vendor risk reassessment

6.4 Partnership Relationship Management (Ongoing)

- Quarterly executive business reviews (IHEP VP Business Development + partner CEO)

- Weekly ops calls (first 3 months); bi-weekly after

- Monthly check-ins addressing issues, escalations, opportunities

- Quarterly outcome and financial reporting

- Annual partner conference (optional)

- Feature partner as IHEP success story (case studies, presentations, media)

### Timeline Summary

| Phase | Duration | Key Deliverables |
| --- | --- | --- |
| Step 1 | Week 1–2 | Inquiry, screening, intro call, mutual interest confirmation |
| Step 2 | Week 2–4 | Technical, clinical, compliance assessments; synthesis; decision gate |
| Step 3 | Week 4–8 | Executed DSA, BAA, Part 2 addendum, compliance roadmap |
| Step 4 | Week 6–12 | Interop configured, EHR tested, consent/access designed, training, go-live checklist |
| Step 5 | Week 12–24 | 50–100 patients enrolled, workflows refined, outcomes measured, revenue validated |
| Step 6 | Month 4+ | Expansion roadmap, sustained improvement, long-term partnership |